## Sheet1
TEAM EPSILON
Server Health Monitoring System (SHMS) — Infrastructure Monitoring Platform
Team Capacity and Sprint Allocation
S.No | Member Name | Role | Sprint Focus | Points/ Sprint | Availability | Status
1 | Sai Abhiram | Product Owner & Scrum Master | Backlog, Planning & Sprint Management | 10 | 100% | Active
2 | Vinay Charan | Lead Developer & Solution Architect | System Architecture & Core Development | 14 | 100% | Active
3 | Bandhav | DevOps Engineer | CI/CD, Docker, Deployment & Monitoring | 12 | 100% | Active
4 | Abhiram Krishna | Frontend Developer | Dashboard UI, Real-time Graphs & Alerts UI | 13 | 100% | Active
5 | Navadeep | ML Engineer | Anomaly Detection, Predictive Alerts & Models | 12 | 100% | Active
6 | Prem Kumar | Operations Assistant | Server Config, Infra Support & Docs | 9 | 90% | Active
7 | Nihal | Testing Engineer (QA) | Unit Testing, Integration, QA & Reports | 11 | 90% | Active
SPRINT PLAN — 6 SPRINTS
Sprint # | Sprint Goal | Start Date | End Date | Duration | Committed Pts | Completed Pts | % Done | Velocity | Defects Found | Defects Fixed | Carry Over | Status | Stakeholder Review | Notes
Sprint 1 | Requirements, Architecture & Planning | 2026-06-15 | 2026-06-21 | 7 Days | 70 | 68 | 97% | 68 | 0 | 0 | 2 | Completed | 2026-06-16 | SRS, Architecture Doc, Product Backlog, Sprint Plan completed ✓
Sprint 2 | Core Agent Setup & Data Collection Module | 2026-06-22 | 2026-06-28 | 7 Days | 75 | 75 | 100% | 75 | 3 | 3 | 0 | Completed | 2026-06-23 | Windows Exporter, Prometheus & Grafana (ID 24390) deployed ✓
Sprint 3 | Dashboard UI & Real-time Monitoring | 2026-06-29 | 2026-07-05 | 7 Days | 80 | 12 | 15% | 0 | 0 | 0 | 68 | In Progress | 2026-06-30 | PB-07 completed; refining historical views (PB-08) next
Sprint 4 | ML Anomaly Detection & Smart Alerts | 2026-07-06 | 2026-07-12 | 7 Days | 85 | 0 | 0% | 0 | 0 | 0 | 85 | Planned | 2026-07-07 | Anomaly detection model, predictive alerts, threshold breach warnings
Sprint 5 | DevOps Pipeline, Logging & Notification System | 2026-07-13 | 2026-07-19 | 7 Days | 80 | 0 | 0% | 0 | 0 | 0 | 80 | Planned | 2026-07-14 | GitHub Actions CI/CD, Docker, Email/Slack alerts, log aggregation
Sprint 6 | Testing, Deployment & Project Release | 2026-07-20 | 2026-07-26 | 7 Days | 72 | 0 | 0% | 0 | 0 | 0 | 72 | Planned | 2026-07-21 | Full UAT, regression testing, production deployment
TOTALS |  |  |  |  | 462 | 155 | 35.33% | 23.8333 | 3 | 3 | 307
Sprint 1 Detail — Requirements, Architecture & Planning | [6 empty] | Sprint 1 Summary
Sprint 1 Daily Activity Log
Date | Team Member | Activity Performed | Pts | Help Needed | Status |  | Metric | Value |  | Deliverable | Status
2026-06-15 | Sai Abhiram (PO/SM) | Project kickoff meeting conducted; stakeholder requirement s gathered | 8 | No | Done |  | Sprint Goal | Requirements, Architecture & Planning |  | Software Requirement Specification (SRS) | Completed
2026-06-15 | Vinay Charan (Arch) | High-level architecture drafted; tech stack finalized | 8 | No | Done |  | Sprint Duration | 15 Jun 2026 – 21 Jun 2026 |  | System Architecture Document | Completed
2026-06-16 | Sai Abhiram (PO/SM | Core features identified; SRS document drafted | 8 | No | Done |  | Committed Story Points | 70 |  | Product Backlog | Completed
2026-06-16 | Navadeep (ML) | ML module scope defined; anomaly detection approach discussed | 4 | No | Done |  | Completed Story Points | 68 |  | Sprint Plan | Completed
2026-06-17 | Sai Abhiram (PO/SM | User stories written for Admin, DevOps, and Operations roles | 8 | No | Done |  | Remaining Story Points | 2 |  | User Stories | Completed
2026-06-17 | Bandhav (DevOps) | CI/CD pipeline requirement s and Docker deployment plan discussed | 4 | No | Done |  | Completion Percentage | 0.97
2026-06-18 | Sai Abhiram (PO/SM) | Backlog prioritized based on monitoring criticality | 6 | No | Done |  | Carry Over | 2
2026-06-18 | Prem Kumar (Ops) | Server infrastructur e requirement s documented | 4 | No | Done |  | Status | Completed
2026-06-19 | Entire Team | Requirement review meeting; project scope finalised and approved | 6 | No | Done
2026-06-20 | Sai Abhiram (PO/SM) | Product Backlog and acceptance criteria finalised | 6 | No | Done
2026-06-20 | Nihal (QA) | Test plan and QA strategy prepared for Sprint 1 deliverables | 3 | No | Done
2026-06-21 | Entire Team | Sprint Review with stakeholders ; Sprint 2 activities approved | 3 | No | Done
Sprint 2 Daily Activity Log – Core Agent Setup & Data Collection Module | [9 empty] | Sprint 2 Summary |  |  | Sprint 2 Deliverables
Date | Team Member | Activity Performed | Pts | Help Needed | Status |  |  |  |  | Metric | Value |  | Deliverable | Status
2026-06-26 | Sai Abhiram (PO/SM) | Installed Windows Exporter agent on target nodes; configured Windows Firewall (inbound rule, TCP port 9182) via Admin PowerShell. | 15 | No | Completed |  |  |  |  | Sprint Goal | Core Agent Setup & Data Collection Module |  | Windows Exporter Agent Setup | Completed
2026-06-26 | Bandhav (DevOps) | Set up Prometheus main server; configured prometheus.yml to scrape team_windows_nodes using Tailscale IPs. | 15 | No | Completed |  |  |  |  | Sprint Duration | 22 Jun 2026 – 28 Jun 2026 |  | Prometheus Server Configuration | Completed
2026-06-26 | Sai Abhiram (PO/SM) | Troubleshot Tailscale VPN connectivity issues (restarted background services) to ensure successful scraping. | 10 | Yes | Completed |  |  |  |  | Committed Story Points | 75 |  | Tailscale Zero-Trust Network Setup | Completed
2026-06-26 | Bandhav (DevOps) | Set up Grafana on port 3000; configured Prometheus as the primary data source. | 10 | No | Completed |  |  |  |  | Completed Story Points | 75 |  | Grafana Real-time Dashboard (ID: 24390) | Completed
2026-06-26 | Bandhav & Sai Abhiram | Debugged Grafana dashboard import issues; resolved Linux/Windows dashboard mismatch & 'job' spelling errors (team_windows_nodes). | 15 | Yes | Completed |  |  |  |  | Remaining Story Points | 0 |  | Live Multi-node Metrics Pipeline | Completed
2026-06-26 | Entire Team | Successfully imported Dashboard 24390; verified real-time live metrics (16-core CPU) across multiple target laptops. | 10 | No | Completed |  |  |  |  | Completion Percentage | 100%
[10 empty] | Defects Found | 3
[10 empty] | Defects Fixed | 3
| Sprint 3 Task Board – Sprint Backlog (from Sprint-3 Backlog) | [8 empty] | Carry Over | 0
[10 empty] | Status | Completed
| Task | Assignee | Story Points | Priority | Status | Acceptance Criteria | Dependenci-es
| Design Dashboard UI Wireframes | Abhiram Krishna | 5 | High | Completed | Wireframes approved by Product Owner covering CPU, Memory, Disk & Network panels | None
| Write PromQL queries for CPU/RAM | Vinay Charan | 8 | High | Completed | Queries return accurate live CPU & RAM metrics in Grafana | Prometheus server (Sprint 2)
| Develop React/Grafana Frontend Layout | Abhiram Krishna | 12 | High | Completed | Dashboard renders responsive live graphs for all monitored parameters | Wireframes, PromQL queries
| Configure Grafana Datasource (secure) &Docker | Bandhav | 5 | High | In Progress | Grafana connects to Prometheus over the secured Tailscale network | Tailscale VPN setup (Sprint 2)
| Integrate Disk & Network Panels | Prem Kumar | 8 | Medium | Planned | Disk I/O and Network bandwidth panels display live data | Frontend layout
| Create ML API Endpoints/Placeholders | Navadeep | 10 | Medium | Planned | Placeholder endpoints available for future anomaly-detection integration | None
| Execute UI Cross-browser Testing | Nihal | 8 | Medium | Planned | Dashboard verified on Chrome, Edge & Firefox with no layout defects | Frontend layout complete
| Sprint Documentation & Review Prep | Sai Abhiram | 5 | Low | Planned | Sprint review deck and documentation ready for stakeholder demo | All Sprint 3 tasks
|  | Sprint 3 Task Board – Sprint Backlog (from Sprint-3 Backlog) | [7 empty] | Sprint 3 Planning – Dashboard UI & Real-time Monitoring (In Progress)
|  | Task | Assignee | Story Points | Priority | Status | Acceptance Criteria | Dependencies |  | Sprint 3 Summary |  |  | Sprint 3 Deliverables
|  | Design Dashboard UI Wireframes | Abhiram Krishna | 5 | High | Completed | Wireframes approved by Product Owner covering CPU, Memory, Disk & Network panels | None |  | Metric | Value |  | Deliverable | Status
|  | Write PromQL queries for CPU/RAM | Vinay Charan | 8 | High | Completed | Queries return accurate live CPU & RAM metrics in Grafana | Prometheus server (Sprint 2) |  | Sprint Goal | Dashboard UI & Real-time Monitoring |  | Real-time Dashboard – Live Graphs (PB-07) | Completed
|  | Configure Grafana Datasource (secure) | Bandhav | 5 | High | Completed | Grafana connects to Prometheus over the secured Tailscale network | Tailscale VPN setup (Sprint 2) |  | Sprint Duration | 29 Jun 2026 – 05 Jul 2026 |  | Historical Data View – 1h/24h/7d (PB-08) | In Progress
|  | Develop React/Grafana Frontend Layout | Abhiram Krishna | 12 | High | In Progress | Dashboard renders responsive live graphs for all monitored parameters | Wireframes, PromQL queries |  | Committed Story Points | 80
|  | Integrate Disk & Network Panels | Prem Kumar | 8 | Medium | Planned | Disk I/O and Network bandwidth panels display live data | Frontend layout |  | Completed Story Points | 12
|  | Create ML API Endpoints/Placeholders | Navadeep | 10 | Medium | Planned | Placeholder endpoints available for future anomaly-detection integration | None |  | Remaining Story Points | 68
|  | Execute UI Cross-browser Testing | Nihal | 8 | Medium | Planned | Dashboard verified on Chrome, Edge & Firefox with no layout defects | Frontend layout complete |  | Completion Percentage | 0.15
|  | Sprint Documentation & Review Prep | Sai Abhiram | 5 | Low | Planned | Sprint review deck and documentation ready for stakeholder demo | All Sprint 3 tasks |  | Carry Over (Projected) | 68
[10 empty] | Status | In Progress
Formulas:
Stakeholder Review = (Table4[[#This Row],[Start Date]] +1)

## Sheet2
Sprint 1 Summary – Requirements, Architecture & Planning
Sprint 1 Summary | Column2 | Sprint 1 Deliverables | Column4
Metric | Value | Deliverable | Status
Sprint Goal | Requirements, Architecture & Planning | Software Requirement Specification (SRS) | Completed
Sprint Duration | 15 Jun 2026 – 21 Jun 2026 | System Architecture Document | Completed
Committed Story Points | 70 | Product Backlog | Completed
Completed Story Points | 68 | Sprint Plan | Completed
Remaining Story Points | 2 | User Stories | Completed
Completion Percentage | 0.97
Carry Over | 2
Status | Completed